## README
Last Update | 2018-11-04
Author | Ziyi Huang
Email | huangzi_yi96111@163.com
Description | Parking UCR ( Ziyi Huang)
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
7 | Searching availiable parking lots | As a user, whenever I drive to UCR, I may wonder where can I park my car, which parking lot is still available and how many truck space those parking lots remained. | 2 | 1
1 | GPS and navigation | As a user, whenever I am going to park my car, I would like to know where is the nearest available parking lot and how can I get there. | 5 | 2
2 | Set reminder | As a user, I may already have a plan about when I need to park my car. I would like to set a time in the app, and when the time arrives, the app should send me a reminder to tell me which parking lot are still available for me to park my car. | 5 | 3
| Total |  | 12
Note on C2: Acceptance Criteria: 1. Users can check which parking lot in UCR still has parking spaces 2.Users can check the number of available spaces in each parking lot
Note on C3: Acceptance Criteria: 1.Users can use our app to locate themselves 2. Users can search which is the nearest UCR parking lot 3. Users can user this app to navigate to the parking lot they want to go
Note on C4: Acceptance Criteria: 1. Users can set a time in this app 2.Users can get a notification from our app at about 5 minutes before the time they set, the notification will tell them which parking lot is still available at this time.

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: notification interface design
Task 2: sending notification
Task 3: pass data to notification and dislay data
Note on D2: Design a button by click which people can set a reminder Acceptance Criteria: 1. A button to set time and start notification service
Note on D3: Send a notification Acceptance Criteria: 1. when the time we set is up, users will get a notification from the app. By click the notification, users will go to the front page of our app.
Note on D4: Show real-time data in notification Acceptance Criteria: 1.In our notification, people can see the real-time information about the free parking spaces, so users can get these information without open the app.

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Ziyi Huang | 3
2 | Ziyi Huang | 3
3 | Ziyi Huang

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 12 | 0 | 0 | 12 | 12
1 | 12 | 2 | 2 | 10 | 10
2 | 12 | 5 | 7 | 5 | 5
3 | 12 |  | 7 | 5 | 0