## README
Last Update | 2018-11-04
Author | Ziyi Huang
Email | huangzi_yi96111@163.com
Description | Parking UCR ( Ziyi Huang)
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
7 | Searching availiable parking lots | As a user, whenever I drive to UCR, I may wonder where can I park my car, which parking lot is still available and how many truck space those parking lots remained. | 2 | 1
1 | GPS and navigation | As a user, whenever I am going to park my car, I would like to know where is the nearest available parking lot and how can I get there. | 5 | 2
2 | Set reminder | As a user, I may already have a plan about when I need to park my car. I would like to set a time in the app, and 5 minutes before the set time arrives, the app should send me a reminder to tell me which parking lot are still available for me to park my car. | 5 | 3
| Total |  | 12

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Home Page Design
Task 2: Parking Information Page Design
Task 3: Parking Information API

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | Ziyi Huang | 3
2 | Ziyi Huang
3 | Ziyi Huang

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 12 | 0 | 0 | 12 | 12
1 | 12 | 2 | 2 | 10 | 10
2 | 12 |  | 2 | 10 | 5
3 | 12 |  | 2 | 10 | 0